## Destinations Revisions
Ease My Vacations - Destinations Page: Client Revision Analysis
Source: 'Destination Page - Revision.pdf' ¦ Reviewed against Destinations.jsx, DestinationCard.jsx and destination.schema.ts ¦ Analysed 12 Aug 2026 ¦ I = opening framing, B = closing opportunity
Suggestion | My Comment | Tag | Backend / Schema Change?
I. Framing - make Destinations a discovery and conversion page, not a catalogue | Agree. Worth knowing the page is further along than they think - it already splits India from international, filters by region, and pulls live starting prices out of the package data. What it's actually missing is a reason to be there and somewhere to go next. | Strategic | No
1. Change the hero section | Yes. The h1 currently reads 'Global Canvas' with an eyebrow saying 'Portfolio' - it looks nice and tells a visitor nothing. 'Where Will You Go Next?' is a straight improvement and it's a one-line change. | Cosmetic update | No
2. Add destination search | Needed here, and unlike the blog there's a real case for it now. Half of it exists already - the homepage hero has a working destination autocomplete we can lift straight across. Searching packages and articles too is a bigger job and needs the destination link on blog posts first. | Minor update | Cross-entity search would need a new endpoint
3. Don't display every destination equally - group by region | Already built. Region is an enum on the schema and the page already has an All / Europe / Asia / Middle East / Africa / Oceania / Americas filter, plus a separate India section above it. One mismatch: they want India as its own region and the enum has no such value - India sits under Asia and the page works around it by filtering on country. That's fine, but worth knowing before someone 'fixes' the enum. | Cosmetic update | No
4. Add 'Trending Destinations' | Same issue as the blog document - 'trending' implies we're measuring something and we aren't. It would just be six destinations someone picked. Either add a featured flag so it's honestly editorial, or start tracking views. | Minor update | Yes - featured flag
5. Add 'Popular with Indian Travellers' with 'From INR' | The pricing half is already done - the page computes min, max and package count per destination from live package data, so it can't go stale. That's exactly what they ask for in item 16. What's missing is just the section framing. Also: the whole site targets Indian travellers, so a separate 'Popular with Indian Travellers' section is a bit redundant - I'd call it 'Most Booked'. | Cosmetic update | No
6. Destination cards should carry more information | Agreed, and here's the catch that shapes this whole document: the destination schema has exactly four fields - name, country, region, image. There is nowhere to put 'best for', 'ideal duration' or 'best time'. This one change unlocks half the list. Also flag a live bug: the pricing panel only appears on hover, so on mobile it never opens and the card tells someone who can't hover to 'hover to explore'. | Major update | Yes - the big schema expansion
7. Add travel-style filters | Best feature idea in the document. Needs style tags on destinations (schema again), and it has to share the same vocabulary as the homepage's Holiday Styles and the package pages' 'Perfect For' - otherwise we end up with three lists of traveller types that don't match each other. Settle the taxonomy once, use it everywhere. | Major update | Yes - style tags on destinations
8. Add a 'Best For' indicator | Same field as item 7 - build them together. It's one array with two different renderings, not two pieces of work. | Minor update | Yes - same field as item 7
9. Add duration guidance | Cheap once item 6 lands - one more field. Could even be derived from the average nights across that destination's packages, which keeps it honest and means nobody has to maintain it by hand. | Minor update | Yes - or derive from package data
10. Add a 'From India' perspective (flight time, currency, visa) | Useful, and they've spotted the right risk themselves. Visa information especially cannot be typed onto a card and forgotten - if we add it, it needs an explicit 'last reviewed' date and a named owner, same pattern I suggested for the blog. Honestly, for visa I'd link to the official source rather than restate it and take on the liability. | Major update | Yes - info fields + reviewedAt
11. Create proper destination landing pages | Biggest item here by a distance, and completely greenfield - there is no /destinations/thailand route at all today, only the list page. Related bug worth fixing either way: the Share button on each card builds a /destination/{name} link to a route that doesn't exist, so anyone sharing a destination right now is sending out a broken URL. | Major update | Yes - routes, slug, content model
12. Connect destinations directly to packages | Already works at the list level - clicking a card goes to /packages?destination=X and the card already shows how many packages exist. What's missing is a dedicated page to show them on, which is item 11. So this comes almost free once that lands. | Minor update | No
13. Connect destinations to the blog | Depends on blog posts getting a destination field, which I flagged in that sheet. Do the two together, or this ends up matching on freeform tags and surfacing the wrong articles. | Minor update | Yes - destination field on blog posts
14. Add 'Featured Experiences' | Nice idea and it sells the trip far better than a country name does. More a content job than a build - someone has to write six real experiences per destination. Worth doing for the top eight to ten destinations only, not all of them. | Minor update | Yes - experiences array
15. Add a 'Best Time to Visit' visual | Fine, and their own caveat is the important part - seasonal guidance isn't a rule, especially somewhere like Vietnam where it genuinely varies by region. Store it as free text rather than month ranges so we can write 'varies by region' where that's the truthful answer. | Minor update | Yes - bestTime field
16. Add 'Starting From' pricing strategically | Already live, and built the right way - computed from active packages rather than typed in, so their 'a stale price is worse than no price' warning is handled by design. The only gap is that it's hidden behind hover (see item 6). | Cosmetic update | No
17. Add a 'Compare Destinations' feature later | They've said phase two and I agree. It also needs every destination scored on family, honeymoon and adventure - a lot of subjective data to create and maintain for a feature nobody has asked for yet. The 'Help Me Choose' CTA is the valuable half and that can ship now, since it just opens the existing trip planner. | Minor update | Yes if built properly - rating fields
18. Add customer reviews by destination | Same blocker as the homepage and About sheets - testimonials aren't tagged by destination and there isn't enough volume per destination yet. Build the tagging now, ship the section when the reviews exist. | Minor update | Yes - tag testimonials by destination
19. Add 'Why Book This Destination With Us?' | Static block, and it's the same four USPs as the homepage and the About page. Make it one shared component now rather than a fourth hardcoded copy - we're already repeating this argument in three places with slightly different wording. | Cosmetic update | No
20. Add a 'Plan Your Trip' CTA | Cheap and should be everywhere. The planner modal is already global, so it's just a button. The destination version can pre-fill the destination, which makes it noticeably better than the generic one. | Cosmetic update | No
21. Make the page mobile-first | Important, and there's a concrete bug sitting underneath it: the price panel is hover-only, so the single most commercially useful thing on the card is invisible on mobile. Fix that before worrying about swipeable carousels. | Minor update | No
22. Use destination photography strategically | Fair and free - image already exists per destination, so this is about choosing better ones. Content task, not a dev task. | Cosmetic update | No
23. Add breadcrumbs | Easy and worth having, but pointless until the destination pages from item 11 exist - right now there's nothing to breadcrumb to. Do it as part of that work. | Cosmetic update | No
24. Recommended Destinations page structure | Reasonable, and about half of it exists in some shape already - region grouping, prices, package links. The genuinely new parts are search, style filters and the two CTA blocks. One note: their structure drops the India / international split that's already there and works well. I'd keep it. | Minor update | Rolls up the items above
25. Individual destination-page template | Good template, and standardising it matters more than any single section on it - otherwise every destination page gets built slightly differently. But it assumes a lot of content per destination. I'd build the template and then fill three or four destinations properly rather than thirty half-empty ones. | Major update | Rolls up with item 11
26. URL hierarchy - /destinations/asia/thailand/phuket | I'd push back here. Deep nesting is harder to maintain, and the moment a destination moves region the URL breaks and needs a redirect. Google doesn't reward the extra depth either. Flat /destinations/thailand is simpler and ranks the same - keep region as a filter and a breadcrumb, not a path segment. | Minor update | Yes - slug field
27. Priority list | Sensible. Two adjustments: their #5 (starting prices) is already done, so it comes off the list entirely. And the schema expansion behind item 6 isn't listed anywhere, even though it blocks items 6, 7, 8, 9, 10 and 15 - it should be #1, because almost nothing else can start without it. | Strategic | No
B. The bigger opportunity - Destinations as the central hub | Agree with the direction, and this is the right page to build the site around. Just be realistic about sequencing: the hub only works when destination pages, destination-tagged blog posts and destination-linked packages all exist. Today one of those three is in place. This is a quarter of work, not a sprint. | Strategic | No