## Revision Analysis
EMV Global - Itinerary / Package Page: Client Revision Analysis
Source: 'Itinerary Page - Revision.pdf' ¦ Reviewed against the live codebase (PackageDetails.jsx, PricingWidget.jsx, package.schema.ts, functions/_preview.js) ¦ Analysed 12 Aug 2026
# | Client's Suggestion | Verdict | My Comment | Tag | Priority | Est. Effort | Backend / Schema Change? | Where It Lands
1 | Change the package title (aspirational name + destinations + tagline) | Agree | Good call, and cheap. The hero already renders destinations as a separate pill above the title, so 2 of the 3 layers the client wants already exist — only a short tagline is missing. Important: `slug` is a separate DB field from `title`, so the customer-facing title can change with zero URL or SEO impact. | Minor update | Medium | 0.5 day | Yes - add `subtitle`/`tagline` to schema + admin form | PackageDetails.jsx (hero), package.schema.ts
2 | Add a package summary bar below the title | Partially exists | Roughly 60% already built - hero badges show category, nights/days and destinations. Genuinely missing: transfer type, a 'Customisable' chip and a hero-level CTA. Transfer type is not in the schema (only per-day `transport` free text), so either add a package-level field or hardcode 'Private / SIC' since it is true for all EMV packages. | Minor update | High | 1 day | Yes (small) - `transfers` field or hardcoded | PackageDetails.jsx (heroBadges)
3 | Put the price ABOVE the fold | Strongly agree - biggest real defect | Confirmed, and worse than the client describes. On mobile the right column stacks AFTER the entire left column, so the price appears below description, inclusions, flights, hotels, the full itinerary and notes - effectively the last thing on the page. Separately, PricingWidget is labelled 'Total Estimate', which reads like a firm quote; 'Starting from' is both more accurate and more defensible. | Major update | Critical | 1-2 days | No | PackageDetails.jsx, PricingWidget.jsx, PackageDetails.module.css
4 | Add a 'Why you'll love this trip' section | Agree - and it exposes an existing bug | Worth doing, but note `highlights[]` already exists in the schema and is NOT rendered anywhere on the page - it is silently used only as a fallback for inclusions. We are already losing content that has been entered. Needs restructuring to {icon, title, text} to support the card layout the client drew. | Major update | High | 2-3 days | Yes - restructure `highlights` + admin UI + content backfill | package.schema.ts, AdminPackagesPage.jsx, PackageDetails.jsx
5 | Make the itinerary dramatically easier to scan (timeline) | Agree - but resolve a blocker first | The data already supports this: activities carry time + icon, and `mealsIncluded` / `transport` exist per day but are never rendered. The bigger problem is that the itinerary is currently blur-locked behind a login wall. A scannable timeline is pointless if users must sign in to read it, and the gate directly contradicts item 24. Recommend showing Days 1-2 free and gating the remainder, or removing the gate. | Major update | Critical | 3-4 days | No (fields already exist, just unrendered) | PackageDetails.jsx (itinerary block, lines ~308-428)
6 | Add a visual route map (Krabi -> Koh Samui -> Phuket, 3N¦2N¦3N) | Agree - high impact for low cost | Fully derivable from existing data: `destinations[]` gives the order, `hotels[].nights` + `hotels[].location` give nights per stop. No schema change needed if hotels are entered properly. One caveat: it must hide itself for single-destination packages, otherwise it renders as a pointless one-item strip. | Minor update | High | 1 day | No | New RouteStrip component in components/packageDetails/
7 | Add destination-specific highlights (per city) | Agree in principle, disagree on placement | The SEO argument is real, but this content is destination-level, not package-level - Krabi's highlights are identical in every Krabi package. Store it once on the Destinations model (which already exists in admin) and pull it in by destination name. Duplicating it per package creates duplicate content across pages, which undermines the very SEO benefit it is meant to deliver. | Major update | Medium | 3 days | Yes - extend Destinations model, not Package | AdminDestinationsPage.jsx, destinations module, PackageDetails.jsx
8 | Make inclusions extremely prominent | Already exists - needs a fix, not a build | The 'What's Included' card is already there as a green/red split. The real problem is the inverse of the request: exclusions fall back to a HARDCODED generic list ('Visa fees', 'City taxes', 'Personal expenses', 'Tips') when a package has none - which is exactly the generic list the client warns against. Delete the fallback and make the field mandatory in admin. | Cosmetic update (+ data-integrity fix) | High | 0.5 day | No - remove fallback, add admin validation | PackageDetails.jsx lines 65-67, AdminPackagesPage.jsx
9 | Create a separate 'Not Included' section | Partially agree | Already rendered, just side-by-side rather than as a separate section. Side-by-side is arguably better here: it supports direct comparison and saves vertical space, which item 24 explicitly asks for. Recommend keeping two columns on desktop and stacking on mobile instead of splitting into a distinct section. | Cosmetic update | Low | 0.25 day | No | PackageDetails.module.css (.inclGrid)
10 | Add hotel information (name, stars, nights, meal plan) | Already largely done | The accommodation card is the strongest part of the page today - name, star rating, room type, address, check-in/out and nights all render. Only genuinely missing: `mealPlan` (stored in the schema, shown in the day-view but not in the hotel card) and the '4-star or similar / subject to availability' disclaimer, which is worth adding for expectation-setting and dispute avoidance. | Minor update | Medium | 0.5 day | No | PackageDetails.jsx (hotels block, lines ~223-305)
11 | Add a 'Customize this package' button everywhere | Strongly agree - best value-per-effort item in the document | Nothing on the page currently says 'customise'; the CTAs are 'Request Quote', 'Inquire About This Package' and 'Chat on WhatsApp'. This is essentially copy plus one button, and it is the clearest differentiator against mass-market OTAs. An `open-travel-quiz` modal event already exists in the codebase and can be reused directly as the customise flow. | Minor update | High | 1 day | No | PackageDetails.jsx, PricingWidget.jsx
12 | Add a sticky booking/enquiry panel (desktop card + mobile bottom bar) | Agree - confirmed missing | Verified: the right column has no `position: sticky` in the CSS, so the pricing card scrolls away permanently, and there is no mobile bottom bar at all. On mobile this is the single largest conversion loss on the page. Should ship together with item 3 as one piece of work rather than separately. | Major update | Critical | 1-2 days | No | PackageDetails.module.css (.right/.sideStack), new StickyQuoteBar
13 | Primary CTA should not simply be 'Book Now' | Agree - already aligned in substance | The page never says 'Book Now', so the client's concern is already addressed. What IS wrong is inconsistency: three different labels ('Request Quote', 'Inquire About This Package', 'Chat on WhatsApp') for what is effectively one action, which dilutes the primary path. Standardise on 'Get My Personalised Quote' as primary, customise as secondary, WhatsApp as tertiary. | Cosmetic update | Medium | 0.25 day | No | PackageDetails.jsx, PricingWidget.jsx
14 | Add a very short enquiry form (modal) | Strongly agree | Correct diagnosis. 'Inquire About This Package' currently does a full page navigation to /contact, which drops the user out of package context and loses scroll position. The backend already exists (POST /leads plus an admin leads screen), so this is front-end only. Keep it to a maximum of 5 fields - the client's list of 6 is already at the limit where completion rates start dropping. | Major update | Critical | 2-3 days | No - `POST /leads` already exists | New QuoteModal component, api.js (createLead)
15 | Add 'Can I customise this package?' / 'Make This Trip Yours' | Agree - cheapest win in the document | Entirely static content, identical across every package, with no schema or admin work required. One hardcoded component. Should be bundled with item 11 and shipped in the same pass rather than tracked as separate work. | Cosmetic update | High | 0.5 day | No | New CustomiseSection component
16 | Add 'Perfect For' (couples / families / friends) | Agree - partially derivable | `category` (Honeymoon / Family / Luxury / Domestic / Wellness) already provides one audience tag for free. A multi-select `perfectFor[]` is better since most packages suit 2-3 audiences. The field earns its keep beyond this section - it becomes a filter on the packages listing page later, which is a bigger win than the badge row itself. | Minor update | Medium | 1 day | Yes - add `perfectFor[]` + admin multi-select | package.schema.ts, AdminPackagesPage.jsx, PackageDetails.jsx
17 | Add difficulty / pace information (dot meters) | Agree in principle - recommend deprioritising | Weakest ROI item in the document. It requires three subjective 1-5 ratings to be judged and then maintained per package, and the dot meters convey little that the words 'Relaxed' or 'Moderate' would not. Recommend a single 'Trip style' tag line instead - which item 16 already proposes - and skipping the meters entirely. | Minor update | Low | 1 day | Yes - 3 numeric fields | package.schema.ts, PackageDetails.jsx
18 | Add 'Important Information' accordion (visa, currency, best time) | Agree - same placement objection as item 7 | `notes[]` already exists and renders as 'Important Notes'. But visa rules, currency, best time to travel and document requirements are country-level facts, not package-level. They belong on the Destinations model and should be pulled in, not retyped per package - retyping is precisely how stale or wrong visa information ends up published. Cancellation policy should be a single site-wide link, not per-package text. | Major update | Medium | 2-3 days | Yes - extend Destinations model | Destinations module, PackageDetails.jsx
19 | Add reviews specific to this destination | Agree - but blocked on data, not code | Testimonials currently exist only as a homepage component with no destination or package tagging, so there is nothing to filter on yet. This needs a tagging field plus enough genuine reviews per destination - otherwise the same two testimonials appear on every Thailand page, which reads worse than showing none. Build the tagging now, ship the section when review volume supports it. | Major update | Medium | 2-3 days + content | Yes - tag testimonials by destination/package | Testimonials model, AdminHomeContentPage.jsx, PackageDetails.jsx
20 | Add a 'You may also like' section | Agree - easy and worth it | Straightforward: query packages sharing a category or destination, exclude the current one, cap at 3-4. The PackageCard component already exists and can be reused as-is with no restyling. Delivers on two fronts - funnel retention and internal linking for SEO. | Minor update | Medium | 1 day | No - existing packages API supports it | PackageDetails.jsx, reuse PackageCard component
21 | Add a strong final CTA before the footer | Agree | Static section, no data dependency, no schema work. One note on expectations: once the sticky panel from item 12 is live, this band becomes reinforcement rather than the last chance to convert - still worth having, but it does not warrant heavy design investment. | Cosmetic update | Medium | 0.5 day | No | New FinalCTA component
22 | SEO improvements (title, H1, meta description, proper H2s) | Agree on the advice - but flag a blocker the client is unaware of | The heading advice is valid and there is a real defect: the page runs h1 -> h3 -> h4 and never uses h2 at all. The far bigger issue is invisible from the browser - this is a client-rendered SPA, and the edge function serves non-browser crawlers a near-empty page containing only meta tags and a redirect, with no itinerary, inclusions or headings in the HTML. Perfecting H2 structure is wasted effort until crawlers receive real content (SSR or proper prerendering). Also needs per-package metaTitle/metaDescription fields; the title is currently auto-generated from the package name. | Major update | Critical (blocker) / Medium (headings) | 1 day headings, 5+ days SSR | Yes - metaTitle/metaDescription fields + rendering strategy | functions/_preview.js, functions/package-details/[id].js, usePageMeta.js
23 | Add FAQ schema | Agree on FAQs - correct the client on the schema benefit | Worth adding, but set expectations correctly: Google removed FAQ rich results for the overwhelming majority of sites in August 2023, so FAQPage JSON-LD will not produce dropdown snippets for EMV. The FAQs remain valuable for on-page conversion, objection handling and AI/LLM answer surfaces - just do not sell it internally as a rich-result win. The crawler-rendering blocker from item 22 applies here too. | Minor update | Medium | 1-2 days | Yes - add `faqs[]` field + admin UI | package.schema.ts, PackageDetails.jsx
24 | Avoid making the page too long before the first CTA | Strongly agree | The current order is Description -> Inclusions -> Flights -> Hotels -> Itinerary -> Notes, which buries the itinerary (the actual product being sold) beneath inclusions and hotels - the exact anti-pattern the client describes. Their proposed order is better. This is pure JSX reordering with no data changes, making it one of the fastest high-impact fixes available on the whole list. | Minor update | Critical | 0.5 day | No | PackageDetails.jsx (section order)
W | Recommended package-page wireframe | Sound and implementable | Essentially the current page reordered plus five new sections, so it is realistic rather than a rebuild. One gap: the wireframe has no slot for flight details, which the schema supports and some packages populate. Recommend inserting flights between Itinerary and Inclusions, rendered only when present. | Major update (template rework) | High | Rolls up items 1-24 | Rolls up above | PackageDetails.jsx (full template)
S | The biggest strategic change (consultant selling, not PDF itinerary) | Agree with the direction | The positioning is right and the Inspire -> Inform -> Build Trust -> Demonstrate Value -> Personalise -> Convert sequence is a good spine for the template. The one thing in the current build that directly contradicts it is the login wall over the itinerary - you cannot inspire or build trust while the product is hidden behind a sign-up. That is a business decision, not a design one: measure whether the leads captured by the gate outweigh the conversions it costs before keeping it. | Strategic / Non-code | Critical (decision required) | Decision, not build | N/A | Business decision - affects itinerary gate in PackageDetails.jsx

## Summary & Rollout
Summary, Cross-Cutting Findings & Suggested Rollout
1. Breakdown by tag
Tag | Count | Items | What it means
Major update | 10 | 3, 4, 5, 7, 12, 14, 18, 19, 22, W | Schema/backend change, new data model, or a substantial UI rebuild.
Minor update | 10 | 1, 2, 6, 10, 11, 16, 17, 20, 23, 24 | Front-end component work, sometimes one small schema field.
Cosmetic update | 5 | 8, 9, 13, 15, 21 | Copy, CSS, reordering, or a static hardcoded section.
Strategic / Non-code | 1 | S | A business decision that must be made before design work lands.
2. Cross-cutting findings the client's document does not mention
# | Finding | Impact | Recommended action
A | The day-by-day itinerary is blur-locked behind a login wall. | Directly contradicts revisions 5, 24 and the overall 'inspire then convert' strategy. Users cannot evaluate the product before signing up. | Decide deliberately: show Days 1-2 free and gate the rest, or remove the gate. Measure leads gained vs conversions lost.
B | `highlights[]` is stored in the DB but never rendered on the page - it is only used as a silent fallback for inclusions. | Content the team has already entered is invisible to customers. Also means revision 4 is partly a bug fix, not a new build. | Render highlights, or restructure the field as part of revision 4.
C | Exclusions fall back to a hardcoded generic list when a package has none. | This is exactly the generic inclusion/exclusion list the client warns against in revisions 8 and 9, shipping automatically. | Delete the fallback and make exclusions a required field in the admin package form.
D | Crawlers that are not browsers receive a near-empty HTML page (meta tags plus a redirect), with no page content. | Blocks the entire SEO intent of revisions 22 and 23. H2 structure and FAQ schema cannot help pages whose content Google may never see in the HTML. | Decide on a rendering strategy (SSR or full prerender) before investing further in on-page SEO work.
E | Heading hierarchy runs h1 -> h3 -> h4; h2 is never used. | Weakens document outline for both SEO and screen readers. | Convert section card titles to h2 as part of revision 22.
F | Three different labels exist for what is effectively one action. | Dilutes the primary conversion path and makes analytics harder to read. | Standardise per revision 13: primary quote CTA, secondary customise, tertiary WhatsApp.
3. Suggested rollout - sequenced by value delivered per day of work
Phase | Items | Why this order | Rough duration
Phase 1 - Quick wins | 24 (reorder), 8 (fallback fix), 13 (CTA wording), 15 + 11 (customise section & button), 9, 21 | All copy, CSS or reordering. No schema work, no backend. Delivers most of the perceived improvement in the first pass. | ~3 days
Phase 2 - Conversion core | 3 (price above fold), 12 (sticky panel), 14 (quote modal), 2 (summary bar) | This is where enquiry volume actually moves. Backend for leads already exists, so it is front-end only. | ~1 week
Phase 3 - Product storytelling | 5 (itinerary timeline), 6 (route strip), 4 (why you'll love), 10, 16, 20 | Makes the page sell rather than document. Item 5 depends on the gate decision (finding A) being made first. | ~1.5 weeks
Phase 4 - Content & SEO infrastructure | 22 (rendering strategy), 7, 18 (destination-level content), 23 (FAQs), 19 (tagged reviews), 1, 17 | Highest effort and partly blocked on content and an architecture decision. Do not start item 23 before item 22 is resolved. | ~2-3 weeks
4. Overall verdict on the client's document
The document is unusually good client feedback - it is specific, commercially motivated and mostly implementable as written. Roughly a third of it describes things that already exist on the page (items 8, 9, 10, 13 and partly 2), which suggests the client reviewed a package with thin data entered rather than a fully populated one; that is worth confirming before scoping. The three recommendations worth acting on fastest are 3 (price above the fold), 12 (sticky panel) and 24 (section reordering) - together they are under a week of work and address the page's real conversion weakness. The one recommendation to push back on is 17 (pace meters): high maintenance burden, low customer value. The one thing to correct the client on is 23 - FAQ schema no longer produces rich results for commercial sites, so the FAQs should be justified on conversion grounds, not SEO ones. Finally, the most consequential issue is not in the document at all: the login wall over the itinerary (finding A) undermines the 'travel consultant selling the holiday' positioning the client closes with. That decision should be made before design work begins.